## Лист1
Task | Responsible | 2017
|  | Jan | Apr | Jun | July |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct | Nov | Dec
[5 empty] | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39
First Project intro
Project idea formalization
Project prototype test
1. Marketing | Alexandre Yurchak | bar: July 28 to Aug 35
1.1 Big client involvement | Alexandre Yurchak | bar: July 28 to Aug 35
1.1.1 UGV | Alexandre Yurchak | bar: July 28 to Aug 35
1.1.1.1 Initial meeting | Alexandre Yurchak |  |  |  | July 28: 13
1.1.1.2 Test tender selection | Sergii Onischenko | bar: July 29
1.1.1.3 Test tender digitalization | Maksym Romanov | bar: July 30
1.1.1.4 Test tender run | Sergii Onischenko | bar: Aug 31
1.1.1.5 Impact visualization | Maksym Romanov | bar: Aug 32
1.1.1.6 Expirience standartization | Sergii Onischenko | bar: Aug 33
1.1.1.7 Project adoption | Maksym Romanov | bar: Aug 34
1.1.1.8 Gathering feedback | Maksym Romanov | bar: Aug 35
1.1.2 UZ | Alexandre Yurchak | bar: July 29 to Aug 35
1.1.3 UOP | Alexandre Yurchak | bar: July 29 to Aug 35
1.2 General market analytics | Maksym Romanov | bar: July 29 to Aug 35
1.2.1 KPIs formalization | Maksym Romanov | bar: July 29
1.2.2 Dashboard preparation | Maksym Romanov | bar: July 30
1.2.3 Promotion plan creation | Alexandre Yurchak | bar: Aug 31
1.2.4 Promoting results | Alexandre Yurchak | bar: Aug 32 to Aug 34
1.2.5 Gathering feedback | Maksym Romanov | bar: Aug 35
1.3 Market players ranking | Maksym Romanov | bar: July 29 to Aug 35
1.2.1 KPIs formalization | Maksym Romanov | bar: July 29
1.2.2 Dashboard preparation | Maksym Romanov | bar: July 30
1.2.3 Promotion plan creation | Alexandre Yurchak | bar: Aug 31
1.2.4 Promoting results | Alexandre Yurchak | bar: Aug 32 to Aug 34
1.2.5 Gathering feedback | Maksym Romanov | bar: Aug 35
2. Legalization | Igor Gavrilov | bar: July 27 to July 30
2.1 Procedure organization | Igor Gavrilov | bar: July 29
2.1.1 Initial TK meeting | Alexandre Yurchak |  |  |  | July 29: 18
2.2 Content preparation | Maksym Romanov | bar: July 27 to July 30
2.2.1 Draft preparation | Maksym Romanov | bar: July 27
2.2.2 Sending for comments | Maksym Romanov | bar: July 28
2.2.3 Comments collection | Maksym Romanov | bar: July 29
2.2.4 Final doc preparation | Maksym Romanov | bar: July 30
3. Partnership | Alexandre Yurchak | bar: July 29
3.1 eClass EU | bar: July 29
3.2 AML | bar: July 29
3.3 ODC winners 2.5 | bar: July 29
3.4 Andrii project | bar: July 29
4. Technical implementation | Maksym Romanov | bar: July 29 to Aug 32
4.1 Data load | Maksym Romanov | bar: July 29
4.2 NLP | Maksym Romanov | bar: July 30
4.3 Rules engine | Maksym Romanov | bar: Aug 31
4.4 Dashboard | Maksym Romanov | bar: Aug 32